## 5x5 Matrix
S5 Risk Matrix:
This matrix addresses risks for S5 within the activity that could impact its successful execution. It does not address risks to the ExEP posed by lack of success of S5.
|  | Likelihood of Risk Occurrence | 5 | [5 empty] | > 60%
|  |  | 4 |  |  | T11 | P7 |  | 30-60%
|  |  | 3 |  |  | P4 | T12 |  | 10-30%
|  |  | 2 |  | T3 | T9 | T5 | T10 | 1-10%
|  |  | 1 |  | P5 | T4, T8 |  | T2 | < 1%
|  |  |  | 1 | 2 | 3 | 4 | 5
Consequence of Risk Occurrence
Likelihood Ratings |  |  | Consequence Ratings
1 | < 1% |  | 1 | Minor design margin loss, < $50K cost, minimal slip on non-critical path
2 | 1 - 10% |  | 2 | Minor mission performance loss, < $150K, < 2 mo. Slip on non-critical path
3 | 10 - 30% |  | 3 | Out of spec but still meets min. mission success criteria with margin, or
4 | 30 - 60% |  |  | requires a small new technology, < $500K, < 2-3mo. slip on non-critical path, or
5 | > 60% |  |  | reduced but acceptable critical path reserve
|  |  | 4 | A mission objective is not achieved, but still meets min. mission success criteria
with little margin, or requires a moderate new technology, < $2M or threatens
recommended reserve, schedule slip that threatens a Level 1 delivery
|  |  | 5 | Does not meet min. mission success criteria, or requires a major new technology,
> $2M, or exceeds available reserves, schedule slip that exceeds reserves
and precludes a Level 1 delivery

## Prog Risk SIP
S5 Risk # | ExEp Risk # | Ratings |  | Risk Stattement | Status
|  | Likeli-hood | Conse-quence
P4 | 99 | 3 | 3 | Delayed production of MDL test masks could threaten M2 | Production is behind schedule. Potential supplemental production by UCSD
P5 |  | 1 | 2 | Edge segment production could threaten later petal level milestones | Schedule has robust margin, pathfinder edges were delivered on schedule, an alternate vendor exists
P7 | 97 | 4 | 4 | Loss of key personnel due to JPL workforce shortage could threaten all milestones | Ongoing concern, though JPL is over the peak problem

## Tech Risk SIP
S5 Risk # | ExEp Risk # | Ratings |  | Risk Stattement | Status
|  | Likeli-hood | Conse-quence
T2 | 88 | 1 | 5 | Bright lobes from solar scatter may not be acceptable to mission study teams | Pending official response from study teams, but reports are essentially complete
T3 | 89 | 2 | 2 | Dust sensitivity or LV environment could threaten M3 | Preliminary characterization tests show insensitive to additional diffuse relections.
T4 | 90 | 1 | 3 | Optical edges must be grounded to avoid discharge | Expect grounding to b e straightforward
T5 | 91 | 2 | 4 | Princeton testbed perf. Limits could threaten M2 | Polarization problem under investigation
T8 | 94 | 1 | 3 | Stray sunlight through micrometeoroid holes could drive more complex optical ahield design | Preliminary analysis shows large margin
T9 | 95 | 2 | 3 | Stray sunlight through optical shield closeout seams between petals and disk could drive OS design | Part of new opacity task
T10 | 96 | 2 | 5 | Solar scatter with out of plane petals | Part of new opacity task
T11 | 102 | 4 | 3 | Truss longeron may not be adequately tuned to match petal CTE, requiring design iteration to thrreaten M6A | May be sufficient to adjust with metal fittings, or to show compliance by analysis
T12 | 103 | 3 | 4 | Bright polarization lobes and variable asymmetry may preclude M2 | Tests are underway to confirm asym. Caused by combination of misalignment and variable mask thickness. Polarization levels should be reduced by fewer petal mask also under test.